## Man Hour
Category | Task List | Activity Details | Estimate (Hours) | Buffer (Hours)
Wordpress Server | Server Creation and Environment Setup | Provision server | 1 | 1
|  | OS update | 0.5
|  | install required packages | 1
|  | configure firewall and users | 0.5
| Database Creation and Testing | Install MySQL/MariaDB | 0.5 | 1
|  | create database and user | 1
|  | test database connectivity | 0.5
| DNS Setting and Securing Web Server | Configure DNS | 1 | 1
|  | install Apache/Nginx | 1
|  | SSL certificate setup | 1
|  | security hardening | 1
| Source Code Deployment and Testing | Install WordPress | 1 | 1
|  | configure application | 2
|  | deploy source code | 1
|  | perform testing | 1
| Documentation | Prepare installation | 0.5 | 1
|  | configuration | 0.5
|  | and handover documentation | 1
Total |  |  | 16 | 5