## Manhour
Server Installation Manhour
Category | Task List |  | Duration (Hour) | Working Day
Frontend Server | 1. Server Creation and Environment Setup | 3 | 21
| 2. DNS Setting and Securing Web Server | 3
| 3. Source Code Deployment and Testing | 4
| 4. Documentation | 2
| 5. Performance Optimization & CDN Setup | 2
| 6. Security Hardening | 2
| 7. Monitoring & Log Alerting | 2
| 8. Backup & Recovery Setup | 2
| 9. Handover & Client Training | 1
Backend Server | 1. Server Creation and Environment Setup | 3 | 26
| 2. DNS Setting and Securing Web Server | 3
| 3. Source Code Deployment and Testing | 5
| 4. Documentation | 2
| 5. Queue Worker & Scheduler Setup | 3
| 6. API Integration Testing | 3
| 7. Security Hardening | 2
| 8. Monitoring & Log Alerting | 2
| 9. Backup & Recovery Setup | 2
| 10. Handover & Client Training | 1
Total |  |  | 47